## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Brian | Connor | Ruby | Shelby | Thomas | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Iteration 1:
Preparation | Architecture |  |  |  |  | 21 |  | 21
|  | ER Diagram | Database Designer | Thomas | 7 |  | 7 | [5 empty] | 7
|  | Wireframes | UI/UX Designer | Brian | 7 |  | 7 |  | 7 | 0 | 0 |  |  | 0
|  | Blazor Demo | Web AI Designer, Integration Lead | Connor, Shelby | 7 |  | 7 |  | 0 | 5 | 0 | 2 |  | 7
| Requirements |  |  |  |  | 10 |  | 14 | [5 empty] | 0
|  | Gather | Integration Lead | Shelby | 5 |  | 6 |  | 2 | 2 | 0 | 6 | 2 | 10
|  | Analyze | Integration Lead | Shelby | 4 |  | 4 |  | 2 | 2 | 0 | 4 | 2 | 8
|  | Specify | Integration Lead | Shelby | 1 |  | 4 |  | 1 | 1 | 0 | 2 | 1 | 4
| Documentation |  |  |  |  | 10 |  | 11 | [5 empty] | 0
|  | Project Charter | Project Manager | Ruby | 2.5 |  | 3 |  | 0 | 0 | 3 |  |  | 3
|  | Iteration 1 Retrospective | Project Manager | Ruby | 2.5 |  | 2.5 |  |  |  | 2.5 |  |  | 2.5
|  | Requirements Document | Project Manager | Ruby | 5 |  | 5.5 |  |  |  | 5.5 |  |  | 5.5
Total |  |  |  |  | 41 | 41 | 47 | 46 | 12 | 10 | 11 | 14 | 12 | 59