## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Brian | Connor | Ruby | Shelby | Thomas | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Iteration 1:
Preparation | Architecture |  |  |  |  | 21 |  | 21
|  | ER Diagram | Database Designer | Thomas | 7 |  | 7 | [5 empty] | 7 | 7
|  | Wireframes | UI/UX Designer | Brian | 7 |  | 7 |  | 7 | 0 | 0 |  |  | 7
|  | Blazor Demo | Web AI Designer, Integration Lead | Connor, Shelby | 7 |  | 7 |  | 0 | 5 | 0 | 2 |  | 7
| Requirements |  |  |  |  | 10 |  | 27 | [5 empty] | 0
|  | Gather | Integration Lead | Shelby | 5 |  | 12 |  | 2 | 2 | 0 | 6 | 2 | 12
|  | Analyze | Integration Lead | Shelby | 4 |  | 10 |  | 2 | 2 | 0 | 4 | 2 | 10
|  | Specify | Integration Lead | Shelby | 1 |  | 5 |  | 1 | 1 | 0 | 2 | 1 | 5
| Documentation |  |  |  |  | 10 |  | 11 | [5 empty] | 0
|  | Project Charter | Project Manager | Ruby | 2.5 |  | 3 |  | 0 | 0 | 3 |  |  | 3
|  | Iteration 1 Retrospective | Project Manager | Ruby | 2.5 |  | 2.5 |  |  |  | 2.5 |  |  | 2.5
|  | Requirements Document | Project Manager | Ruby | 5 |  | 5.5 |  |  |  | 5.5 |  |  | 5.5
Iteration 2: | [13 empty] | 0
Prototype | Development |  |  |  |  | 34 |  | 28 | [5 empty] | 0
|  | Set up databases as described in ER Diagram | Database Designer | Thomas | 10 |  | 10 |  |  |  |  | 0 | 10 | 10
|  | Create Login Screen (Front End) - Add UI elements | UI/UX Designer | Brian | 7 |  | 7 |  | 7 | 0 |  | 0 | 0 | 7
|  | Create Login Screen (Back End) - Add Login functionality | Web AI Designer | Connor | 7 |  | 7 |  | 0 | 7 |  |  |  | 7
|  | Connecting front end and back end of Login Screen | UI/UX Designer, Web AI Designer | Brian, Connor | 2 |  | 4 |  | 2 | 2 |  |  |  | 4
| Analysis |  |  |  |  | 8 |  | 8 | [5 empty] | 0
|  | Research on System Testing | Testing Lead | Shelby | 3 |  | 3 |  | 0 | 0 | 0 | 3 |  | 3
|  | Evaluate needs for next iteration | All | Ruby, Shelby | 5 |  | 5 |  | 1 | 1 | 1 | 1 | 1 | 5
| Documentation |  |  |  |  | 9 |  | 11 | [5 empty] | 0
|  | Software Project Management Plan | Project Manager | Ruby | 5 |  | 7 |  |  |  | 6 |  | 1 | 7
|  | Risk Management Report | Project Manager | Ruby | 4 |  | 3 |  | 0 | 0 | 3 |  |  | 3
|  | Iteration 2 Retrospective | Project Manager | Ruby | 1 |  | 1 |  |  |  | 1 |  |  | 1
Iteration 3: | Design |  |  |  |  | 5 |  | 5 | [5 empty] | 0
Product Development |  | Create new Schema Diagram | Database Designer | Thomas | 2 |  | 1 |  | 0 | 0 |  |  | 1 | 1
|  | Design Home Page | UI/UX Designer | Brian | 2 |  | 3 |  | 3 | 0 | 0 |  |  | 3
|  | Design User Registration Screen | UI/UX Designer (our Integration Lead helped with this task, despite it not being their official role) | Shelby, Brian | 1 |  | 1 |  | 0.25 |  |  | 0.7 | 0 | 0.95
| Development |  |  |  |  | 25 |  | 28.5 | [5 empty] | 0
|  | Recreate databases from Iteration 2 in Microsoft SQL | Database Designer | Thomas | 4 |  | 4 |  |  |  |  | 0 | 4 | 4
|  | Connect databases to Blazor Server using Dapper | Web AI Designer, Database Designer | Connor, Thomas | 2 |  | 3 |  |  | 2 |  | 0 | 1 | 3
|  | Implement Authorization in Login In Screen | Integration Lead | Shelby | 3 |  | 3 |  |  |  |  | 3 | 0 | 3
|  | Implement functionality into User Registration Screen | Integration Lead | Shelby | 3 |  | 2 |  |  |  |  | 2 |  | 2
|  | Implement Home Page Design | UI/UX Designer | Brian | 6 |  | 6 |  | 6 | 0 |  | 0 |  | 6
|  | Display transaction information from database on home page (ongoing) | Web API Designer, Database Designer UI/UX Designer | Connor, Thomas, Brian | 4 |  | 6 |  | 0.5 | 2 |  | 2 | 1.5 | 6
|  | Implement Hamachi for database hosting | Database Designer | Thomas | 1 |  | 2.5 |  |  |  |  | 0 | 2.5 | 2.5
|  | Add hover animations to screens for improved user experience | UI/UX Designer | Brian | 2 |  | 2 |  | 2 | 0 |  | 0 |  | 2
| Documentation |  |  |  |  | 7 |  | 12 | [5 empty] | 0
|  | Architecture Design Document | Project Manager | Ruby | 6 |  | 5 |  | 0 | 0 | 5 |  |  | 5
|  | Iteration 3 Retrospective | Project Manager | Ruby | 1 |  | 1 |  |  |  | 1 |  |  | 1
|  | Midterm Presentation - Design Slides and Practice | Project Manager, All Team | Ruby, All Team | 3 |  | 6 |  | 1 | 1 | 2 | 1 | 1 | 6
Iteration 4: | Design |  |  |  |  | 3.5 |  | 4 | [5 empty] | 0
Product Development continued |  | Design pages around password retrieval | UI/UX Designer (our Integration Lead helped with this task, despite it not being their official role) | Shelby | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 1
|  | Design Settings Page | UI/UX Designer | Brian | 2.5 |  | 3 |  | 3 | 0 | 0 |  |  | 3
| Development |  |  |  |  | 26 |  | 28 | [5 empty] | 0
|  | Implement Settings Page Design | UI/UX Designer | Brian | 7 |  | 8 |  | 8 |  |  |  | 0 | 8
|  | Implement functionality and design of Password Retrieval Page | UI/UX Designer (our Integration Lead helped with this task, despite it not being their official role) | Shelby | 5 |  | 6 |  |  |  |  | 6 | 0 | 6
|  | Create form for adding transactions | Web AI Designer, Database Designer | Connor, Thomas | 8 |  | 8 |  |  | 4 |  |  | 4 | 8
|  | Create database entries from the add transaction form | Database Designer | Thomas | 6 |  | 6 | [5 empty] | 6 | 6
| Analysis |  |  |  |  | 9 |  | 13 | [5 empty] | 0
|  | Research writing tests with Blazor | Testing Lead | Shelby | 3 |  | 5 |  |  |  |  | 5 | 0 | 5
|  | Nofication implementation research | Database Designer | Thomas | 3 |  | 4 | [5 empty] | 4 | 4
|  | Email Notification implementation research | Web AI Designer | Connor | 3 |  | 4 |  |  | 4 |  |  |  | 4
| Documentation |  |  |  |  | 18 |  | 10 | [5 empty] | 0
|  | Test Plan (To be completed next iteration) | Project Manager, Testing Lead | Ruby, Shelby | 5 |  | 3 |  | 0 | 0 | 3 |  |  | 3
|  | User Manual (To be completed next iteration) | Project Manager | Ruby | 6 |  | 3 |  |  |  | 3 |  | 0 | 3
|  | Administrator's Guide (To be completed next iteration) | Project Manager | Ruby | 6 |  | 3 |  |  |  | 3 |  | 0 | 3
|  | Iteration 4 Retrospective | Project Manager | Ruby | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 1
Iteration 5: | Design |  |  |  |  | 5 |  | 6 | [5 empty] | 0
Product Development completed |  | Redesign Setting-Notifications Screen | UI/UX Designer (our Project Manager helped with this task, despite it not being their official role) | Brian, Ruby | 1 |  | 1 |  | 0.5 | 0 | 0.5 |  | 0 | 1
|  | Design notifications UI | UI/UX Designer | Brian | 2 |  | 3 |  | 3 | 0 | 0 |  |  | 3
|  | Redesign Login Screens | UI/UX Designer | Brian | 1 |  | 1 |  | 1 | 0 | 0 |  |  | 1
|  | Redesign Home Screen | UI/UX Designer (our Project Manager helped with this task, despite it not being their official role) | Brian, Ruby | 1 |  | 1 |  | 0.5 |  | 0.5 | 0 | 0 | 1
| Development |  |  |  |  | 29.5 |  | 37 | [5 empty] | 0
|  | Implement Notifications in Database | Database Designer | Thomas | 10 |  | 10 |  |  |  |  | 0 | 10 | 10
|  | Add email notification functionality | integration Lead, Database Lead | Shelby, Thomas | 3 |  | 5 |  |  | 0 |  | 4 | 1 | 5
|  | Add functionality to export transaction reports | Web AI Designer | Connor | 3 |  | 3 |  |  | 3 |  | 0 | 0 | 3
|  | Implement Settings-Notification Screen Design | UI/UX Designer | Brian | 2.5 |  | 3 |  | 3 |  |  | 0 |  | 3
|  | Implement Home Page Design | UI/UX Designer | Brian | 4 |  | 6 |  | 6 | 0 |  | 0 |  | 6
|  | Implement Notifications UI | Integration Lead, UI/UX Designer, Database Designer | Shelby, Thomas, Brian | 4 |  | 6.5 |  | 2 | 0 |  | 3 | 1.5 | 6.5
|  | Implement Reset Password Functionality in Application | Integration Lead | Shelby | 1 |  | 1.5 |  |  |  |  | 1.5 | 0 | 1.5
|  | Fix Add Transactions functionality | UI/UX Designer, Web AI Designer | Brian, Connor | 2 |  | 2 |  | 1 | 1 |  | 0 |  | 2
| Documentation |  |  |  |  | 5 |  | 9 | [5 empty] | 0
|  | Test Plan | Project Manager, Web API Designer | Ruby, Connor | 4 |  | 4.5 |  | 0 | 2 | 2.5 |  |  | 4.5
|  | Iteration 5 Retrospective | Project Manager | Ruby | 1 |  | 1 |  |  |  | 1 |  |  | 1
|  | Final Presentation - Design Slides and Practice | Project Manager, All Team | Ruby, All Team | 4 |  | 3.5 |  | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 3.5
Total |  |  |  |  | 225 | 225 | 258.45 | 258.5 | 63.25 | 39.5 | 46 | 47.7 | 62 | 258.45